# SIH 2026 – PS 26027: AI-Powered Automatic Block Planning

## Full Solution Blueprint (PPT-ready → Prototype-ready)

## 0. How to use this document

- Now → Aug 27, 8 PM: Sections 1–8 give you everything to write the PPT.

- Aug 27 → 29: Sections 9–11 give you the exact build plan for the working prototype/demo.

- Section 12 is a slide-by-slide skeleton you can paste straight into PowerPoint.

## 1. Reframe the Problem (this is what judges actually care about)

Strip the jargon and the real problem is:

Three departments (Engineering/P.Way, TRD, S&T) each ask for "block time" (track/traffic closure windows) independently, on paper/manual coordination via BDMS. Nobody is jointly optimizing which maintenance gets done when, on which corridor, using whose block window — so blocks get wasted, clash, or get under-utilized, and trains get delayed or assets stay defective longer than needed.

So the AI system you're building is fundamentally a multi-agent resource-scheduling and prioritization problem, not a generic "AI dashboard." Judges will reward you for treating it as an optimization problem with an ML-driven priority layer on top, not just a CRUD app with a chatbot bolted on.

Three sub-problems to solve, in order:

- What needs to be done, and how urgently? (prioritization / scoring)

- When and where can it be done given track possession/corridor availability? (feasibility / constraint matching)

- What's the best overall assignment of tasks → block windows across all 3 departments? (optimization/scheduling)

## 2. High-Level Architecture

┌─────────────────────────────────────────────────────────────────────┐

│                         DATA INGESTION LAYER                         │

│  TMS (track defects) │ SMMS (signal faults) │ TDMS (OHE/traction)    │

│  COA (corridor/block availability) │ Train Time Table │ Goods forecast│

└───────────────────────────────┬───────────────────────────────────────┘

│  (REST/CSV/DB connectors + adapters)

▼

┌─────────────────────────────────────────────────────────────────────┐

│                     UNIFIED DATA MODEL (the real IP)                 │

│  Normalizes all 3 departments' maintenance items into one schema:    │

│  Asset ID, Section/Corridor, Defect type, Severity, Overdue-days,    │

│  Est. duration, Crew/resource need, Precedence, Dept, Safety class   │

└───────────────────────────────┬───────────────────────────────────────┘

▼

┌───────────────────────────┐   ┌───────────────────────────────────┐

│  PRIORITIZATION ENGINE     │   │  BLOCK AVAILABILITY ENGINE         │

│  (ML + rule-based scoring) │   │  Extracts free/possible block      │

│  → Urgency/Criticality      │   │  windows per corridor from COA +   │

│    score per task           │   │  timetable + goods forecast        │

└───────────────┬─────────────┘   └───────────────┬─────────────────┘

│                                  │

└───────────────┬──────────────────┘

▼

┌─────────────────────────────────────────────────────────────────────┐

│              OPTIMIZATION / SCHEDULING ENGINE (the core AI)          │

│  Constraint Programming (OR-Tools CP-SAT) + Metaheuristic fallback   │

│  Assigns tasks → block windows, maximizing weighted priority         │

│  completed, minimizing conflicts, clubbing compatible blocks across  │

│  departments, respecting precedence/resource/safety constraints      │

└───────────────────────────────┬───────────────────────────────────────┘

▼

┌─────────────────────────────────────────────────────────────────────┐

│                    OUTPUT / PLANNING LAYER                            │

│  Weekly block plan (tactical) │ Monthly block plan (strategic)        │

│  Gantt/corridor-timeline dashboard │ Conflict alerts │ What-if sim     │

│  Asset-availability & downtime KPIs │ Exportable block request forms  │

└─────────────────────────────────────────────────────────────────────┘

## 3. Data Layer — what "integration" actually means here

You will not get live access to real TMS/SMMS/TDMS/COA systems (they're internal Railway systems). That's fine — every SIH team is in the same boat. The trick is to build a clean adapter layer + realistic synthetic dataset and say explicitly in the PPT: "Designed with pluggable connectors; demonstrated on a realistic synthetic dataset modeled on actual RDSO/BDMS field formats."

Build a canonical schema all three feeds map into:

| Field | Example |
| --- | --- |
| task_id | ENG-2291 |
| department | Engineering / S&T / TRD |
| asset_id | Track Km 42.3–43.1, Down line |
| section/corridor | CSTM–Pune |
| defect_type | Rail fracture risk / Signal relay fault / OHE tension defect |
| severity | Priority I/II/III (use actual Railway severity classes) |
| overdue_days | 12 |
| est_duration_min | 90 |
| crew_required | 6 |
| precedence | must follow task X |
| safety_class | Safety-critical / Essential / Routine |
| last_inspection_date | — |
| failure_risk_score | ML-predicted |

Corridor/block side, from COA + timetable + goods forecast:

| Field | Example |
| --- | --- |
| corridor_id | CSTM–Pune Down |
| window_start / window_end | 01:00–03:30 |
| available_capacity | max concurrent work-parties |
| traffic_density_score | derived from timetable + goods forecast (how costly is closing this window) |

This "traffic density / opportunity cost" score is a nice touch — it lets your optimizer prefer blocks that cause the least train-operation disruption, directly answering the "maximize asset availability without hurting train ops" ask in the PS.

## 4. Prioritization Engine (AI/ML layer #1)

Two-stage design — this is a strong technical talking point:

Stage A — Predictive risk scoring (ML): Train a model (Gradient Boosting / XGBoost, or simpler Random Forest to keep it explainable to non-ML judges) to predict probability of asset failure / service impact if maintenance is deferred by N more days, using features like defect severity, overdue days, asset age, traffic load on that section, past failure history. This is essentially a lightweight predictive maintenance / survival-analysis flavored model.

Stage B — Multi-Criteria priority score (explainable, judge-friendly): Combine the ML risk score with rule-based weights (Railways will always want an explainable, auditable score, not a black box):

Priority Score = w1*Severity + w2*Overdue_days(normalized)

+ w3*ML_failure_risk + w4*Safety_class_weight

+ w5*Traffic_criticality_of_section

Weights configurable by Railway officials (a slider in the dashboard) — this is a great "human-in-the-loop, not full automation" story to tell judges, since Railways will never fully trust a black-box scheduler with safety.

## 5. Optimization/Scheduling Engine (AI/ML layer #2 — the real core)

This is the differentiator vs. teams that only build a dashboard. Frame it explicitly as an optimization problem:

- Decision variables: assign each maintenance task to a specific block window (or leave unscheduled this cycle).

- Objective: maximize Σ(priority_score × task_scheduled) − penalty×(conflicts) − penalty×(train delay caused).

- Constraints:

  - A block window can't be double-booked beyond its capacity.

  - Precedence constraints (Task B needs Task A done first).

  - Crew/resource availability constraints.

  - Safety separation rules (can't run two conflicting possessions on adjacent lines simultaneously if unsafe).

  - Cross-department block clubbing: if Engineering and S&T both need the same corridor closed, merge into one combined block instead of two separate closures → this is a genuine efficiency win you can quantify.

Solver choice (say this explicitly in the PPT — it shows technical maturity):

- Weekly horizon (short-term, smaller task set): exact solve using Google OR-Tools CP-SAT (Constraint Programming) — fast, provably optimal or near-optimal at this scale.

- Monthly horizon (larger, more tasks/corridors): CP-SAT is likely too slow → use a metaheuristic (Genetic Algorithm or Simulated Annealing) to get a good-enough schedule quickly, then let CP-SAT locally refine hot spots.

- Dynamic re-planning: when a new emergency defect appears mid-week, don't re-solve from scratch — use an incremental greedy insertion + local re-optimization so the whole plan doesn't churn. You can mention an RL-based adaptive re-scheduler as a future roadmap item rather than building it now (RL is overkill for a 2-day-to-PPT hackathon and hard to demo convincingly).

This gives you a clean, honest technical story: rule-based + ML priority scoring → constraint optimization for scheduling → metaheuristics for scale → human override.

## 6. Multi-Horizon Planning Output

- Weekly plan: tactical, corridor-by-corridor Gantt/timeline, granular block windows, used by section engineers.

- Monthly plan: strategic rollup, shows planned major blocks/mega-blocks, used for coordination with commercial/traffic dept in advance (Railways plans mega-blocks weeks ahead).

- Both should be regenerable on demand and support what-if simulation: "what if we get an extra 2-hour block on Sunday night?" → shows re-optimized plan and marginal benefit (this is a great live-demo moment).

## 7. Tech Stack (concrete, defend-able choices)

| Layer | Tech |
| --- | --- |
| Data ingestion / adapters | Python, Pandas, FastAPI |
| Database | PostgreSQL (relational, good for constraint queries) |
| ML prioritization | scikit-learn / XGBoost |
| Optimization engine | Google OR-Tools (CP-SAT), fallback DEAP (genetic algorithm) |
| API layer | FastAPI |
| Frontend dashboard | React + Tailwind, Gantt via a library (e.g., frappe-gantt or a custom D3 timeline) |
| Visualization | Recharts / D3 for KPIs, corridor-timeline view |
| Deployment (for demo) | Docker Compose, or just run locally for hackathon demo |

Keep this stack — it's realistic to build a working, demoable slice of this in ~48 hours for the internal round, which matters because judges distinguish "PPT vaporware" from "team that clearly can execute."

## 8. Synthetic Dataset Plan (do this first, before anything else)

Since there's no real data access:

- Generate ~150–300 synthetic maintenance tasks split across the 3 departments, with realistic severity/overdue distributions (skew: most Routine, few Priority-I safety-critical).

- Generate ~10–15 corridors with weekly block-window availability derived from a plausible train timetable + goods traffic forecast (make traffic density higher on trunk routes like Mumbai–Delhi, lower on branch lines).

- Inject a few deliberate conflicts (two departments wanting the same corridor at the same time) so your optimizer has something visibly smart to resolve in the demo — this is the single best "wow" moment for judges: show the naive/manual plan with a clash, then show your system's clubbed/optimized plan with the clash resolved and both departments' work still done in a merged window.

## 9. Prototype Build Plan for the Internal Hackathon (Aug 27 evening → Aug 29)

Don't try to build the whole architecture. Build a thin vertical slice that's fully working end-to-end:

Day 1 (Aug 27 night – Aug 28):

- Finalize synthetic dataset (CSV/JSON), unified schema loader.

- Build the priority scoring function (rule-based first; add the ML model only if time permits — a working rule-based score beats a half-broken ML pipeline).

- Build CP-SAT weekly scheduler with the core constraints (capacity, precedence, no double-booking).

Day 2 (Aug 28):

- Build FastAPI endpoints: /tasks, /corridors, /generate-plan?horizon=weekly|monthly.

- Build the React dashboard: table of tasks with priority scores, corridor timeline/Gantt showing the generated block plan, a "conflicts resolved" counter, a KPI panel (asset availability %, blocks utilized %, downtime hours saved vs. naive baseline).

Day 3 (Aug 29, before presenting):

- Add the what-if slider (extra block window → re-optimize).

- Polish UI, rehearse the live demo script (see below), prepare fallback recorded video in case live demo fails.

Live demo script (aim for this exact arc, it sells the AI story):

- Show the messy manual/independent block requests (3 depts, overlapping, some wasted).

- Show the system ingesting & scoring tasks (highlight ML/priority score, explain weighting).

- Click "Generate Weekly Plan" → optimizer runs → show the clean, conflict-free, clubbed schedule.

- Show KPI improvement numbers (e.g., "reduced total block-hours needed by X%, cleared Y more overdue Priority-I defects this week").

- Do a live what-if: add an emergency defect, click re-plan, show it slot in without breaking the rest of the schedule.

## 10. Timeline (from today, Aug 25, to Aug 29)

| Date | Task |
| --- | --- |
| Aug 25 (today) | Finalize this architecture with your team, assign roles, start synthetic data generation |
| Aug 26 | Build core scoring + CP-SAT prototype on paper/notebook (Jupyter) to validate the approach works on your synthetic data; build PPT content in parallel |
| Aug 27 (by 8 PM) | Finalize and submit PPT |
| Aug 27 (night) – Aug 28 | Build working prototype (Section 9 plan) |
| Aug 29 | Polish, rehearse, present at internal hackathon |

## 11. Suggested Team Role Split (adjust to your team size/skills)

- 1 person: Data layer — synthetic dataset generation + unified schema + FastAPI ingestion endpoints.

- 1–2 people: Optimization engine — OR-Tools CP-SAT model, constraints, objective function.

- 1 person: ML prioritization scoring (rule-based first, XGBoost stretch goal).

- 1–2 people: Frontend dashboard — Gantt/timeline, KPI panel, what-if UI.

- 1 person: PPT, demo script, narrative, and judge Q&A prep (this role matters as much as coding — SIH internal rounds are won on clarity of story as much as tech).

## 12. PPT Slide-by-Slide Skeleton

- Title — Problem ID 26027, team name, one-line tagline (e.g., "From decentralized block requests to one coordinated, AI-optimized schedule.")

- Problem Statement — restate PS crisply, 3 bullet pain points (decentralized, manual, poor coordination → downtime + train delays).

- Proposed Solution — Overview — the architecture diagram from Section 2.

- How it Works — Prioritization — Section 4's two-stage scoring, with a simple example (walk through 1 defect getting scored).

- How it Works — Optimization — Section 5, explain CP-SAT/scheduling in plain language with a visual (before/after conflict resolution diagram).

- Multi-Horizon Planning — weekly vs monthly view mockup.

- Tech Stack — Section 7 table, keep it clean/logo-based.

- Feasibility & Data Strategy — be upfront: real integration via pluggable connectors to TMS/SMMS/TDMS/COA; demonstrated on realistic synthetic data modeled on Railway formats; note this is standard practice for hackathon prototypes.

- Impact / KPIs — quantify: reduced block conflicts, higher % of overdue Priority-I defects cleared per cycle, estimated reduction in train-operation disruption (state as illustrative estimates from simulation, don't overclaim real-world numbers).

- Novelty / USP — (a) cross-department block clubbing, not siloed scheduling; (b) explainable, human-tunable priority weights, not a black box; (c) dual-horizon (weekly tactical + monthly strategic) output; (d) what-if simulation for planners.

- Roadmap — Phase 1 (this prototype) → Phase 2 (live TMS/SMMS/TDMS/COA API integration + RL-based adaptive re-scheduling) → Phase 3 (pan-zone rollout).

- Team & Thank You.

## 13. Things to explicitly say (and NOT overclaim) to judges

- Say: "Human-in-the-loop — Railway officials retain override authority; the AI recommends, doesn't auto-execute safety-critical decisions."

- Say: "Priority weights are configurable, auditable, and explainable — critical for a safety-regulated environment."

- Don't claim: real-time integration with actual TMS/SMMS/TDMS/COA (you don't have access) — be upfront it's simulated on realistic synthetic data with a designed adapter layer for real integration.

- Don't claim: fully autonomous decision-making — Railways (and judges familiar with Railway safety culture) will distrust a "fully automatic, no human check" pitch.

Bottom line pitch, one sentence: "We turn three departments' independent, manual block requests into one AI-optimized, conflict-free, explainable weekly-and-monthly schedule that maximizes asset uptime without hurting train operations — validated with a working constraint-optimization prototype, not just slides."